# Project Plan

## Project Goals and Objectives

- Formulate a concept that enables more group workspace in classrooms.

- Ensure that Bocconi students and staff are satisfied with new classroom design.

- Accomplish project goals and objectives within the defined budget and timeline.

- Minimize the impact that construction will have on classes.

## Project Organization

| Roles | Responsibilities | Participants |
| --- | --- | --- |
| Project Sponsors | - Ultimate decision-makers - Review/approve some project elements | Nicolo di Blasi Gabriella Zanga |
| Primary Advisors | - Approves major funding and resource allocation strategies - Resolves conflicts and issues - Provides direction to the Project Manager - Manages project budget | Design Consultants |
| Project Manager | - Manages project in accordance to the project plan - Supervise vendor(s) - Provide overall project direction - Direct team members toward project goals and objectives | Architect |
| Project Participants | - Provide feedback post-construction | Bocconi Students Bocconi Professors |

## Project Approach

|  | Overview | Responsibilities |
| --- | --- | --- |
| Phase I | Comprehensive audit of similar projects done by other universities or the same university in the past | - Primary Advisors: Need to research similar projects in competitive universities. Based on the findings, begin a basic plan for the Bocconi classrooms. |
| Phase II | Development of creative design concepts that will meet the business objectives and then tested with target audience | - Primary Advisors: Need to work with Bocconi administration and architect to formulate a creative design for classrooms. - Project Manager: The architect needs to work with their team of employees to construct a visual design. - Project Sponsors: Approve design concept for construction. |
| Phase III | Focus on the definitive creative design concept, previously approved by those responsible of university infrastructures | - Primary Advisors: Work with the Project Sponsors and the Project Manager to figure out the logistics of the plan. Further critique and improve design plans. - Project Manager: Further develop the design concept. |
| Phase IV | Order all the material and equipment from previously selected suppliers | - Project Manager: Must order all relevant materials and labor for the initial construction phase. |
| Phase V | Follow the construction step-by-step, assisting the architects | - Primary Advisors: Oversee the construction of the classrooms and make sure the budget and timeline are accurately being followed. - Project Manager: Begin construction on the classrooms. |
| Phase VI | Develop measurement metrics | - Primary Advisors: Aid the administration of Bocconi in analyzing the students’ feedback about the new design. Make adjustments where needed. - Project Sponsors: Evaluate the students’ and professors’ opinions about the new classroom design. - Project Participants: Participate in an evaluation of the new design to see if it aids both group work and class participation. |

## Project Budget

| Budget Item | Cost per | Total |
| --- | --- | --- |
| Consultant Fee | € 30.000 – 35.000 x 1 (over entire project) | € 30.000-35.000 |
| Architect Fee | € 40.000 – 50.000 x 1 (over entire project) | € 40.000 – 50.000 |
| Lawyer Fee | € 120 per hour x 36 hours | € 4.320 |
| Materials - Furniture - Lighting - Construction materials | € 190 x 15 tables € 65 x 90 chairs € 40 x 20 lighting fixtures € 30.000 x 1 (materials, tools, etc.) | € 2.850 € 5.850 € 800 € 30.000 |
| Labor | € 2.000 per hour x 8 hours a day x 40 days | € 640.000 |
| Miscellaneous - Unforeseen fees - Extra materials | -- | € 10.000 |
| Total Sample Project Budget |  | € 733.820,00 – 748.820,00 |

## Project Timeline

| Start Date | 11 January 2011 | The design project is initiated. Consultants, administration, and architect begin to develop a new concept for the classroom. | Milestone |
| --- | --- | --- | --- |
| Action 1 | 3 March 2011 | Design concept has been completed and approved by the Project Sponsors. A budget has also been developed and approved. | Milestone |
| Action 2 | 22 April 2011 | Project Sponsors and Primary Advisors work with the lawyers to approve the plans legally. |  |
| Action 3 | 2 May 2011 | All materials and labor are ordered for the beginning construction date. The Primary Advisors and Project Manager review the timeline and budget. |  |
| Midway Point | 4 July 2011 | Construction begins on the classrooms. | Milestone |
| Action 4 | 26 August 2011 | Construction of classrooms is completed. Labor and excess material s are removed from the building. The classrooms are cleaned to begin usage in September. |  |
| Action 5 | 6 October 2011 | An evaluation of the classrooms is performed by the Project Sponsors. The Project Participants are asked to comment on the new design of the classrooms. |  |
| Due Date | 16 December 2011 | All evaluations have been reviewed and final adjustments have been made. | Milestone |

## Constraints

The following are known project constraints:

- Project funding sources are limited.

- Working with an existing structure; Bocconi is not planning on constructing a new academic building

- Academic schedule; not interrupting on-going classes.